## Muncie Family Physicians
SERVICE ORDER DEVELOPMENT MATRIX
| Contractural Requirements (Deliverables) |  | Schedule F Fees and Proposed Adjustments |  | Contractural Time Frames (Project Schedule Development) |  |  | Proposed Project Schedule
|  |  | Clinic Project Size (0-2,500SF) |  | SLA Framework (Working Days)
| Deliverable/Phase | Required | per Contract | Proposed | Phase | Remodel / Expansion
Small Remodel | 4.2.3.1 A Feasibility: Feasibility Kick-off | X | 1100 | 0 |  | per Contract | Proposed
| 4.2.3.1 B Feasibility: Feasibility Scope Interview | X | 3300 | 0 | Project Kick-off | 1 | 1
| 4.2.3.1 D Feasibility: Scenario Development | X | 1650 | 0 | Scope Review | 1 | 1
| 4.2.3.1 C Feasibility: Preliminary Programming | X | 3850 | 0 | Site Due Diligence | 5 | 1
| 4.2.3.1 E Feasibility: Utilization Analyses | X | 3300 | 0 | Preliminary Floor Plan | 5 | 5
| 4.2.3.2 A Schematic Design Phase: Site Due Diligence |  | 6050 |  | Schematic Design Documents | 10 | 5
| 4.2.3.2 B Schematic Design Phase: Programming | X | 4950 | 0 | Design Development Documents | 10 | 10
| 4.2.3.2 D Schematic Design Phase: Preliminary Floor Plan |  | 1650 |  | Construction Documents | 15 | 15
| 4.2.3.2 E Schematic Design Phase: Schematic Design Documents |  | 6050 |  | Permitting/Bidding | 15 | 15
| 4.2.3.3 Design Development Phase |  | 4950
| 4.2.3.4 Construction Development Phase |  | 6050
| 4.2.3.5 A Preconstruction, Bidding and Permitting Phase: Permitting |  | 1980
| 4.2.3.5 B Preconstruction, Bidding and Permitting Phase: Bidding |  | 1980
| 4.2.3.6 Construction Phase |  | 6050
| Muncie Family Physicians | Total: | 34760