## Life Cycle Data Worksheet
General Project Information | [7 empty] | Project Managers | Project Leaders |  | Project Types | Special Types | Compensation | Category
Project Name: |  | Muncie Family Physicians |  |  |  | Project Start Date: | 2026-07-06 | (Select) | (Select) |  | (Select) | (Select) | (Select)
Project Location: |  | (from Initial Information) |  |  |  | Project Number: | (Must be Requested) | Andrea Bowman, AIA | Justin Aubert, AIA |  | Consolidation | (None) | (Schedule E) | If < 10,000S.F.
|  | (from Initial Information) | [5 empty] | Sean Johnson, AIA |  |  | Contraction | Feasibility Stage | (Schedule F) | If < 10,000S.F.
Project Group: |  | (Select) |  |  |  | Project Manager: | (Select) |  |  |  | Expansion | Architectural Site Plan | Percentage Fee
Project Type: |  | (Select) |  |  |  | Project Leader: | (Select) |  |  |  | New Site | Preliminary Site Plan | Stipulated Fee
Special Type: |  | (Select) |  |  |  | UHG DE Regional Rep.: | (from Initial Information) |  |  |  | Ground Up | One-off | Negotiated Fee
Compensation: |  | (Select) |  |  |  | UHG Regional PM Rep.: | (from Initial Information) |  |  |  | Tenant Build-out | Infrastructure/MDF
Current Project Status | [10 empty] | Remodel/Renovation | Refresh
Current Phase: |  | (Select) |  | Issue(s): | Deficiency Report | [5 empty] | Relocation
Completion %: |  | (Consult w/Project Leader) | [8 empty] | Split-Relocation
Completion Date: |  | (from Design Schedule)
At Risk: |  | (Select)
Scope Description | [7 empty] | Phases |  | Design Consultants |  | Architect's Supplemental Services
(from Initial Information) Must be refined/discussed to create clear understanding in Project Initiation Phase | [7 empty] | (Select) |  | (Select) |  | (Select)
[8 empty] | Project Initiation |  |  |  | 3D scanning services/digital imaging and associated travel/management
[8 empty] | FS -Kick-off |  |  |  | Field Measurement and Site Due Diligence Report
[8 empty] | FS_Scope Interview |  |  |  | Civil Engineering
[8 empty] | FS-Preliminary Program |  |  |  | Landscape Design
[8 empty] | FS-Scenario Development |  |  |  | MEP Engineering
[8 empty] | FS-Utilization Analysis |  |  |  | On-Site Project Representation
[8 empty] | Schematic Design |  | Supplemental Service Consultants |  | Commissioning
Project S.F.: |  | Existing (S.F.): | (TBD) |  | % of Existing |  |  | Design Development |  | (Architect) |  | Sustainable Project Services pursuant to Section 3.1.3
| xx,xxx | New (S.F.): | (TBD) |  | Conditions Reused: |  | (Requested Data) | Construction Documents |  | Consultant |  | Historic Preservation
Project Sustainability Objectives | [7 empty] | Bidding/Permitting |  |  |  | Other Services provided by Specialty Consultants
(from Initial Information) | [7 empty] | Construction Administration |  |  |  | Post Occupancy Evaluation
[8 empty] | Project Close-out |  |  |  | Other Supplemental Services (Listed Below):
[6 empty] | Certification Req'd.: | (Select) | Post Occupancy
Budget (Cost of the Work) |  |  |  | Project Schedule Information (Initial) |  |  |  | Warranty Period
Original COW: |  | (from Initial Information) |  | Project Start Date: |  |  | 46209
DD COW: |  | (TBD) |  | Design Start Date: |  |  | (Date of Purchase Order) | Owner's Consultants and Contractors
CD COW: |  | (TBD) |  | Design Completion Date: |  |  | (from Design Schedule) | (Select)
Bid Amount: |  | (TBD) |  | Construction Start Date: |  |  | (from Initial Information) | Furniture
Final COW: |  | (TBD) |  | Substantial Completion Date: |  |  | (from Initial Information) | Flooring
Sound Masking
Design Consultants (Basic Services) |  |  |  | Supplemental Consulting Services (if Required) |  |  |  | Artwork/Branding
Mechanical: |  | (Select) |  | (Select) |  |  | (Architect) | Security (Owner internal and Business teams)
Contact: |  |  |  | (Select) |  |  | (Architect) | Audio Visual
Electrical: |  | (Select) |  | (Select) |  |  | (Architect) | Signage
Contact: |  |  |  | (Select) |  |  | (Architect) | Medical Equipment
Structural: |  | (Select) |  | (Select) |  |  | (Architect) | IT/Technology/Low Voltage (Owner internal and Business teams)
Contact: |  |  |  | (Select) |  |  | (Architect) | Storefront Systems
Owner's Consultants | [7 empty] | Food Service
(Select) |  |  |  | (Select)
(Select) |  |  |  | (Select)
(Select) |  |  |  | (Select)
(Select) |  |  |  | (Select)
(Select) |  |  |  | (Select)
(Select) |  |  |  | (Select)

## Design Schedule
Project Design Schedule | [7 empty] | Project Design Schedule | [5 empty] | 1.0 SERVICE LEVEL AGREEMENT FRAMEWORK: Timeframe expectations by Project Type (Business Days)
Project Name: |  | Muncie Family Physicians |  |  | Project Start Date: | 46209 |  |  | PROJECT PHASE | DURATION (Days) | DESIGN MILESTONE DELIVERY DATE | ACTUAL DELIVERY DATE | REVISION | The range of business days assumes the lesser number of days applies to the lower end of the square footage
Project Location: |  | (from Initial Information) |  |  | Project Number: | (Must be Requested) |  |  | Owner Progress Review 1 |  |  |  |  | category and the longer time frame applies to the higher end of the square footage category
|  | (from Initial Information) | [6 empty] | (Architectural, Furniture & Medical Equipment, |  |  |  |  | Phase | New Location / Relocation | Remodel / Expansion | Refresh / Infrastructure
Project Group: |  | (Select) |  |  | Project Manager: | (Select) |  |  | and Millwork Elevations) |  |  |  |  | Project Kick-off | 1 | 1 | 1
Project Type: |  | (Select) |  |  | Project Leader: | (Select) |  |  | Peer Design Review 2 |  |  |  |  | Scope Review | 1–5 | 1 | 1
Special Type: |  | (Select) |  |  | UHG DE Regional Rep.: | (from Initial Information) |  |  | Owner Progress Review 2 |  |  |  |  | Scenario Development | 5–10 | 5–10 | 5
Compensation: |  | (Select) |  |  | UHG Regional PM Rep.: | (from Initial Information) |  |  | (Discuss Power & Data Requirements and |  |  |  |  | Utilization Analyses | 2–10 | 2–5 | 1–2
| PROJECT PHASE |  | DURATION (Days) | DESIGN MILESTONE DELIVERY DATE |  | ACTUAL DELIVERY DATE | REVISION |  | design revisions) |  |  |  |  | Site Due Diligence | 5–10 | 5 | 5
| Project Initiation | [7 empty] | QA/QC Review 1 |  |  |  |  | Detailed Programming | 5 | 5 | 5
| Project Kick-off | [7 empty] | Owner Progress Review 3 |  |  |  |  | Preliminary Floor Plan / Schematic Design Documents | 5–10 | 5–10 | 5
| Scope Review/Clarification | [7 empty] | (Finalize Power & Data Plans, Finishes, and |  |  |  |  | Design Development Phase | 15 | 10–15 | 5–10
| Budget Review/Clarification | [7 empty] | design revisions) |  |  |  |  | Construction Docs | 15–20 | 15–20 | 15
| Supplemental and/or Additional Services | [7 empty] | Owner Consultant Coordination |  |  |  |  | Permitting / Bidding | 15–20 | 15 | 15
| Design Schedule | [7 empty] | Design Exceptions (noted or Approved) |  |  |  |  | Some projects may warrant accelerated SLA timelines which will be mutually agreed to by Firm and Owner.
| Site Visit? | [7 empty] | Budget Review/Clarification
| Proposed Compensation | [7 empty] | DD Phase Submittal Date |  |  |  |  | Management of the project schedule, including the internal approval process, is the responsibility of the Owner’s Project Manager, with Architect
| Service Order Submittal Date | [7 empty] | DD Phase Approval Date |  |  |  |  | having responsibility for design delivery components of the overall schedule. The timeframe expectations are intended to be adequate and appropriate
| Service Order Approval Date | [7 empty] | Construction Documents |  |  |  |  | for Architect to deliver its services to an acceptable level by the owner to move forward. Incomplete data, untimely additions, or untimely approvals
| Site Planning Services | [7 empty] | Construction Documents |  |  |  |  | may result in extensions of the project schedule. However, incomplete drawings, missed design intent or functionality will not warrant additional time
| Project Kick-off | [7 empty] | Specifications |  |  |  |  | to the Architect.
| Document Verification | [7 empty] | Owner's Consultant's Work
| Proposed Compensation | [7 empty] | (Incorporation) |  |  |  |  | From SOW General Services:
| Service Order Submittal DAte | [7 empty] | Life Safety Plan |  |  |  |  | 4.2.1 The Architect shall submit for the Owner's approval a schedule for the performance of the Architect's services, and the services of Owner
| Service Order Approval Date | [7 empty] | 50 % CD Package Review Meeting (ground up Projects only) |  |  |  |  | provided consultants, which initially shall be consistent with the time periods established in SLA Exhibit and which shall be adjusted by mutual
| Design Documentation | [7 empty] | up Projects Only) |  |  |  |  | written agreement if necessary, as the project proceeds. This schedule shall include allowances for periods of time required for Owner's review,
| Architectural/Preliminary Plan Submittal Date | [7 empty] | Final Cost of Work Adjustments |  |  |  |  | the performance of the Owners consultants, and for approval of submissions by authorities having jurisdiction over the Project. Time limits
| Architectural/Preliminary Plan Approval Date | [7 empty] | Preparation of Bidding Information (w/DE) |  |  |  |  | established by the Schedule approved by the Owner shall not, except for reasonable cause, be exceeded by the Architect or the Owner.
| Feasibility Stage Services | [7 empty] | Clash Detection
| Feasibility Kick-off | [7 empty] | Final Code Review |  |  |  |  | From SOW Basic Services:
| Feasibility Scope Interview | [7 empty] | QA/QC Review 2 |  |  |  |  | As soon as practicable after the date of the Service Agreement, the Architect shall submit for the Owner’s approval a schedule for the performance
| Preliminary Program | [7 empty] | 90% CD Package Review Meeting (as determined by Owner) |  |  |  |  | of the Architect’s services complying with the Owner’s preliminary schedule. The schedule initially shall include anticipated dates for the
| Scenario Development | [12 empty] | commencement of construction and for Substantial Completion of the Work as set forth in the Initial Information. The schedule shall include
| Utilization Analysis | [7 empty] | Final Pick-ups |  |  |  |  | commencement of construction and for Substantial Completion of the Work as set forth in the Initial Information. The schedule shall include
| Feasibility Phase Submittal Date | [7 empty] | CD Phase Submittal Date |  |  |  |  | allowances for periods of time required for the Owner’s review, for the performance of the Owner’s consultants, and for approval of submissions by
| Feasibility Phase Approval Date | [7 empty] | CD Phase Approval Date |  |  |  |  | authorities having jurisdiction over the Project. Once approved by the Owner, time limits established by the schedule shall not, except for reasonable
| Schematic Design | [6 empty] | Bidding and Permitting Phase | [5 empty] | cause, be exceeded by the Architect or Owner. With the Owner’s approval, the Architect shall adjust the schedule, if necessary, as the Project proceeds
| Site Due Diligence Report | [7 empty] | Bid Time |  |  |  |  | until the commencement of construction.
| Field Measurement | [7 empty] | Permit Submittal
| Program Summary Document | [7 empty] | Permit Review/Response |  |  |  |  | The Design Milestone Dates are the dates by which the Architect shall be obligated to complete each phase of its design
| Preliminary Code Review | [7 empty] | Permit Received |  |  |  |  | services for each building or other segment of the Project and are a component of the Design Schedule. The Architect
| Preliminary Floor Plan | [7 empty] | Bid Date |  |  |  |  | acknowledges and agrees that performing its services in accordance with the Design Milestone Dates is important to the
| Preliminary Floor Plan Approval | [7 empty] | Actual Bid Date |  |  |  |  | timing and success of the overall Project.
| Schematic Design Documents | [7 empty] | Contract Negotiations
| Peer Design Review 1 | [7 empty] | Construction Start Date
| Design Exceptions | [7 empty] | Actual Construction Start Date
| Budget Review/Clarification | [7 empty] | Substantial Completion
| SD Phase Submittal Date | [7 empty] | Actual Substantial Completion Date
| SD Phase Approval Date | [7 empty] | Final Payment
| Design Development | [7 empty] | Warranty Period
| DD Documents | [7 empty] | Warranty Period Conference
| Specifications | [7 empty] | Project Completion Date
MEP Narrative

## Compensation
Project Compensation Data | [7 empty] | Project Managers | Project Leaders |  | Project Types | Special Types | Compensation | Category
Project Name: |  | Muncie Family Physicians |  |  |  | Project Start Date: | 46209 | (Select) | (Select) |  | (Select) | (Select) | (Select)
Project Location: |  | (from Initial Information) |  |  |  | Project/S.O. Number: | (Must be Requested) | Andrea Bowman, AIA | Justin Aubert, AIA |  | Consolidation | (None) | (Schedule E) | If < 10,000S.F.
|  | (from Initial Information) | [5 empty] | Sean Johnson, AIA |  |  | Contraction | Feasibility Stage | (Schedule F) | If < 10,000S.F.
[11 empty] | Expansion | Architectural Site Plan | Percentage Fee
[11 empty] | New Site | Preliminary Site Plan | Stipulated Fee
Fee for Basic Servces (Architectural and Interior Design) | [10 empty] | Ground Up | One-off | Negotiated Fee
Project S.F.: |  | Compensation | [8 empty] | Tenant Build-out | Infrastructure/MDF
| xx,xxx |  | Feasibility Stage |  | SD Thru DD |  | CD Thru Closeout |  |  |  | Remodel/Renovation | Refresh
|  | Stipulated Sum | Enter | Amount | Enter | Amount | (Enter Amount) |  |  |  | Relocation
|  | Percentage Basis | N/A |  | Enter | % | (Enter Percentage) |  |  |  | Split-Relocation
|  | Other | Enter | N.T.E. | Enter | N.T.E. | (Enter Amount) N.T.E.
Design Consultants Compensation
|  | Basis for Compensation | or | Enter Amount
Mechanical | [7 empty] | Phases |  | Design Consultants |  | Architect's Supplemental Services
[8 empty] | (Select) |  | (Select) |  | (Select)
Electrical | [7 empty] | Project Initiation |  |  |  | 3D scanning services/digital imaging and associated travel/management
[8 empty] | FS -Kick-off |  |  |  | Field Measurement and Site Due Diligence Report
Structural | [7 empty] | FS_Scope Interview |  |  |  | Civil Engineering
[8 empty] | FS-Preliminary Program |  |  |  | Landscape Design
Civil (if Required) | [7 empty] | FS-Scenario Development |  |  |  | MEP Engineering
[8 empty] | FS-Utilization Analysis |  |  |  | On-Site Project Representation
Basic Service Exception (if any) | [7 empty] | Schematic Design |  | Supplemental Service Consultants |  | Commissioning
[8 empty] | Design Development |  | (Architect) |  | Sustainable Project Services pursuant to Section 3.1.3
[8 empty] | Construction Documents |  | Consultant |  | Historic Preservation
Supplemental Consulting Services (if Required) | [7 empty] | Bidding/Permitting |  |  |  | Other Services provided by Specialty Consultants
|  | Basis for Compensation | or | Enter Amount |  |  |  | Construction Administration |  |  |  | Post Occupancy Evaluation
[8 empty] | Project Close-out |  |  |  | Other Supplemental Services (Listed Below):
Post Occupancy
Warranty Period
Additional Services (if any)
|  | Basis for Compensation | or | Enter Amount |  |  |  | Owner's Consultants and Contractors
(Select)
Furniture
Flooring
Sound Masking
Artwork/Branding
Security (Owner internal and Business teams)
Audio Visual
Reimbursable Expenses (Travel, Permit Fees and/or Field Office) | [7 empty] | Signage
Medical Equipment
IT/Technology/Low Voltage (Owner internal and Business teams)
Storefront Systems
Food Service

## Service Order
AIA Document B221 - Service Order | [6 empty] | AIA Document B221 - Service Order |  |  |  | AIA Document B221 - Service Order
Service Order No.: |  | Provided by CBRE PM | [5 empty] | Feasibility Phase: | Schematic through | Construction Development | Other Supplemental Services (Listed Below): |  |  |  |  | Responsibility
Service Order Date: |  | Use Date of Project Engagement Meeting | [6 empty] | Design Development | through Closeout Services: | List Other Service(s) |  |  |  | Not Provided
Phase:
Owner: | United HealthCare Services, Inc. | [5 empty] | Basic Services
| 9700 Healthcare Lane | [5 empty] | Consultants:
| Minnetonka, MN 55343 | [5 empty] | (MEP&Structural)
Architect: | Grace Healthcare Studios, LLC |  |  | Grace Healthcare Studios USA, LLC |  | One for Mississippi! | (Select) |  |  |  | The Architect shall provide Construction Administration Services exceeding the limits set forth in Exhibit "A" Scope of
| 501 Government Street | [9 empty] | Work as Additional Services: |  | (Not sure what to put here)
| Suite 200 | [5 empty] | (Select) |  |  |  | ARTICLE 3 DATE OF COMMENCEMENT AND SUBSTANTIAL COMPLETION
| Baton Rouge, LA 70802 | [9 empty] | Commencement of Construction Date: |  |  | (from Initial Information)
Need to Verify which states require which corporation name (per Legal) | [6 empty] | (Select) |  |  |  | Substantial Completion Date: |  |  | (from Initial Information)
Project Name: | Muncie Family Physicians | [9 empty] | ARTICLE 4.1 COMPENSATION |  | (per Exhibits E & F of B121)
Location: | (from Initial Information) | [5 empty] | Supplemental Services | [5 empty] | Feasibility Phase: |  | Schematic through | Construction Development
| (from Initial Information) | [5 empty] | Consultants: | [5 empty] | (if applicable) |  | Design Development | through Closeout Services: | Compensation (From Exhibits E or F)
Project Description: | [6 empty] | (Architect) | [7 empty] | Phase: |  | N/A
(from Initial Information) Must be refined/discussed to create clear understanding in Project Initiation Phase | [6 empty] | (Architect) |  |  |  | Stipulated Sum |  | (Insert Amount) |  | N/A | N/A | (Insert Amount)
[7 empty] | (Architect) |  |  |  | (Insert Amount) | [5 empty] | (Insert %)
[7 empty] | (Architect) |  |  |  | Percentage Basis |  | N/A |  | (Insert %) | (Insert %)
[7 empty] | (Architect) |  |  |  | (Insert % Amount) |  |  |  | % of the Owner's budget for the Cost of the Work, as
Master Agreement Dated: |  |  | 2025-10-14 | Line 1 of B121 - 2018 |  |  | (Architect) | [7 empty] | calculated in accordance with Section 4.4
|  |  | 2026-01-01 | Article 1.1 B121 - 2018 |  |  | ARTICLE 2 SERVICES UNDER THIS SERVICE ORDER |  |  |  | Other
ARTICLE 1 INITIAL INFORMATION | [6 empty] | Basic Services Exceptions: |  |  |  | (Describe Method)
Initial Information: |  | See Attachment "X": Project Scope Document |  |  |  |  | Feasibility Phase Exceptions: | (NONE) or List
|  | See Attachment "X": Project Design Schedule | [8 empty] | 4.2 For Additional Services:
Sustainable Objective: |  | (from Initial Information) |  |  |  |  | SD thru DD Exceptions: | (NONE) or List |  |  | (Basis of Compensation) |  | See Attachment "X" Additional Services and/or Reimbursable Expenses
Certification Required: |  | (Select) | [8 empty] | 4.3 Reimbursable Expenses: |  | See Attachment "X" Additional Services and/or Reimbursable Expenses
[7 empty] | CD thru Closeout Exceptions: | (NONE) or List |  |  | (Amount of Compensation)
|  |  | Feasibility Phase: |  | Schematic through | Construction Development |  |  |  |  | 4.4 | Needs Editing - Percentages do not equal 100%
[5 empty] | Design Development | through Closeout Services: |  |  |  |  | ARTICLE 5 INSURANCE |  | (per B121 Master Agreement)
[5 empty] | Phase: |  | Supplemental and Additional Services: |  |  |  | ARTICLE 6 PARTY REPRESENTATIVES
Owner's Consultants: | [8 empty] | Responsibility |  | UHG Design Experience Regional Representative:
(Select) | [6 empty] | Supplemental Services |  | (Architect, Owner or Not Provided) |  | (Name, address, contact info.) |  | (from Initial Information)
(Select) | [6 empty] | 3D scanning services/digital imaging and associated |  | Not Provided |  | UHG Regional Project Management Representative:
(Select) | [6 empty] | travel/management |  |  |  | (Name, address, contact info.) |  | (from Initial Information)
(Select) | [6 empty] | Field Measurement and Site Due Diligence Report |  | Not Provided |  | Architect Project Management Representative:
(Select) | [6 empty] | Civil Engineering |  | Not Provided |  | (Name, address, contact info.) |  | (Select)
(Select) | [6 empty] | Landscape Design |  | Not Provided |  | Architects Project Representative:
(Select) | [6 empty] | MEP Engineering |  | Not Provided |  | (Name, address, contact info.) |  | (Select)
(Select) | [6 empty] | On-Site Project Representation |  | Not Provided |  | ARTICLE 7 ATTACHMENTS AND EXHIBITS
(Select) | [6 empty] | Commissioning |  | Not Provided |  | Other Exhibits incorporated into this Agreement:
(Select) | [6 empty] | Sustainable Project Services pursuant to Section 3.1.3 |  | Not Provided |  | Attachment "X" - Project Scope Document
(Select) | [6 empty] | Historic Preservation |  | Not Provided |  | Attachment "X" - Project Design Schedule
(Select) | [6 empty] | Other Services provided by Specialty Consultants |  | Not Provided |  | Attachment "X" - Additional Services and/or Reimbursable Expenses
[7 empty] | Post Occupancy Evaluation |  | Not Provided |  | Other Documents:
[7 empty] | Other Supplemental Services (Listed Below): |  |  |  | (TBD)
Responsibility
Architect
Owner
Not Provided

## Project Tracking Report
Project Tracking Report | [6 empty] | Project Tracking Report |  | Design Fee Reporting (Quarterly)
Project Name: | Muncie Family Physicians |  |  |  | Project Start Date: | 2026-07-06 | Potential Project Risk and proposed Mitigation Strategies |  | Format should match or exceed level of detail in Exhibit J and include any Owner requested changes
Project Location: | (from Initial Information) |  |  |  | Project/S.O. Number: | (Must be Requested) |  | (Per Phase) | Design Fees including all consultants by project, reimbursable costs and any additional services:
Proposed/Budgeted Fees vs actual Fees per project:
Project Group: | (Select) |  |  |  | Project Manager: | (Select) |  |  | Number of Staff and time spent on Owner's account: Per Phase)
Project Type: | (Select) |  |  |  | Project Leader: | (Select)
Special Type: | (Select) |  |  |  | UHG DE Regional Rep.: | (from Initial Information)
Compensation: | (Select) |  |  |  | UHG Regional PM Rep.: | (from Initial Information)
Current Project Status | [8 empty] | The total number of requests and projects handled.
Current Phase: | (Select) |  | Issue(s): | Deficiency Report |  |  |  |  | The percentage of requests that met the expected response times.
Completion %: | (Consult w/Project Leader) | [5 empty] | Deficiency Report |  | Project name
Completion Date: | (from Design Schedule) | [6 empty] | (Per Phase) | Brief description
At Risk: | (Select) | [7 empty] | Percentage of Existing Conditions/ walls (etc.) reused per project
Scheduled Project phases
Project Tracking per Phase | [8 empty] | Project Status
Project Initiation Phase: | [8 empty] | Service Order requested, submittal dates and approval status
Design Milestone Date: | 0 |  |  |  | Submittal Date: | 0 |  |  | Potential project risk and proposed mitigation strategies
Submittal Attempts: | (Manual Entry) |  |  |  | Approval Date: | 0 |  |  | Project team leader and contact point
Approval Deficiencies: | (Manual Entry from DR) | [7 empty] | Number of Staff and their percentage of time spent on Owner’s account
No. of Staff | (Phase Close-out Data) |  |  |  | % Time spent on account: | (Phase Close-out Data) |  |  | Deficiency report
Feasibility Stage: | [8 empty] | Project was or was not delivered according to the agreed-upon schedule, and budget at the final funding milestone
Design Milestone Date: | 0 |  |  |  | Submittal Date: | 0
Submittal Attempts: | (Manual Entry) |  |  |  | Approval Date: | 0
Approval Deficiencies: | [8 empty] | Architectural and MEP coordination issues/ misses
No. of Staff |  |  |  |  | % Time spent on account: | (Phase Close-out Data) |  |  | Number of Change Orders per project
Schematic Design Phase:
Design Milestone Date: | 0 |  |  |  | Submittal Date: | 0 |  |  | Number of RFIs per project- broken down by type (detailed Owner scope change, unforeseen conditions, Errors and Omissions)
Submittal Attempts: | (Manual Entry) |  |  |  | Approval Date: | 0
Approval Deficiencies: | (Manual Entry from DR)
No. of Staff | (Phase Close-out Data) |  |  |  | % Time spent on account: | (Phase Close-out Data)
Percentage of Existing Conditions/ walls (etc.) reused per project |  |  | (Requested Data)
Design Development Phase:
Design Milestone Date: | 0 |  |  |  | Submittal Date: | 0 | Schedule reduction (savings)
Submittal Attempts: | (Manual Entry) |  |  |  | Approval Date: | 0 |  | (Per Phase)
Approval Deficiencies: | (Manual Entry from DR)
No. of Staff | (Phase Close-out Data) |  |  |  | % Time spent on account: | (Phase Close-out Data)
Percentage of Existing Conditions/ walls (etc.) reused per project |  |  | (Requested Data)
Construction Document Phase:
Design Milestone Date: | 0 |  |  |  | Submittal Date: | 0 | Cost Savings and applied strategies for cost savings
Submittal Attempts: | (Manual Entry) |  |  |  | Approval Date: | 0 |  | (Per Phase)
Approval Deficiencies: | (Manual Entry from DR)
Project delivered on budget:
No. of Staff | (Phase Close-out Data) |  |  |  | % Time spent on account: | (Phase Close-out Data)
Bidding and Permitting Phase:
Number of RFI's | (Manual Entry) | (Assuming we will have a log somewhere)
Coordination issues | (Manual Entry) | (Assuming we will have a log somewhere) |  |  |  |  | Original Design Fees (Including Consultants, Additional Services & Reimbursables):
Number of Addenda | (Manual Entry) | (Assuming we will have a log somewhere) | [5 empty] | (Manual Entry calculated from Approved Service Order)
Permitting Duration | (Manual Entry)
Review/Response Letters | (Manual Entry) | [5 empty] | Approved Revisions
Construction Phase: | [7 empty] | (Document Revisions)
Number of RFI's | (Manual Entry) | (Assuming we will have a log somewhere)
Number of RFC's | (Manual Entry) | (Assuming we will have a log somewhere) |  |  |  |  | Final Design Fees:
Number of Change Orders | (Manual Entry) | (Assuming we will have a log somewhere) | [5 empty] | (Manual Entry)