## WORKFLOW
PROJECT LIFECYCLE WORKFLOW DIAGRAM
DOCUMENT DATE OF RECEIPT
RECEIPT OF REQUEST
IS PROJECT START DATE
NEED TO TRACK EACH REQUEST
(WHETHER APPROVED OR NOT)
Identify Team to receive all requests
Determine Project Group
(Admin. Or Clinical)
Determine Project Manager
Initial Information should Contain:
Project Group |  |  | LCD WORKBOOK
Project Type |  |  | LCD WORKSHEET POPULATES:
Identify "Special" Type (for Fee Structure) |  |  | PROJECT DESIGN SCHEDULE
Scope (Initial) |  |  | SERVICE ORDER TEMPLATE
Project Square Footage (for Fee Calcs) |  |  | PROJECT TRACKING REPORT
(if under 10,000s.f.)
Budget (Initial)
Sustainability Objectives
Project Milestones:
Construction Start Date
Substantial Completion Date |  | NEEDS TO BE CLEARLY DEFINED
Additional Services |  | WE NEED A QUICK TURN AROUND
Supplemental Consulting Services
Owner's Consultants
(Alliance Partners)
Need to Verify there will be a "Kick-off" Meeting
DISCUSS/CLARIFY ALL ITEMS ABOVE |  | Need to Verify if Site Visit is required prior
to execution of Service Order
Performance Metrics:
Service Order requested date, approved date or status
Total number of requests and projects handled (Dashboard)
Percentage of requests that met the expected response times
Number of Submittals Required (First Time Approval Rate)
Approval Deficiencies
Number of Staff and % of time spent on Owner's account
START
REQUEST RECEIPT
INITIAL INFORMATION PROVIDED BY DESIGN EXPERIENCE (OWNER)
PROJECT MANAGER:
CREATE LCD WORKBOOK
ENTER ALL KNOWN DATA ON LCD WORKSHEET
REQUEST PROJECT NUMBER
ASSIGN PROJECT LEADER
EXIT TO LCD WORKSHEET
EXAMPLE
EXIT TO
PROJECT NUMBER REQUEST
(SUB-FLOW)
SCHEDULE PROJECT KICK-OFF MEETING AND/OR SITE VISIT
EXIT TO
PROJECT INITIATION PHASE
SUBMIT SERVICE ORDER FOR APPROVAL
SERVICE ORDER APPROVAL
PROJECT MANAGER:
REVIEW/DOCUMENT
ALL REQUIRED
PERFORMANCE METRICS
EXIT TO
SCHEMATIC DESIGN PHASE
EXIT TO
SITE PLANNING SERVICES
EXIT TO
FEASIBILITY STAGE
SUBMIT PHASE COMPLETION DOCUMENTS
FOR APPROVAL
PHASE APPROVAL
PROJECT MANAGER:
REVIEW/DOCUMENT
ALL REQUIRED
PERFORMANCE METRICS
EXIT TO
DESIGN DEVELOPMENT PHASE
SUBMIT PHASE COMPLETION DOCUMENTS
FOR APPROVAL
PHASE APPROVAL
PROJECT MANAGER:
REVIEW/DOCUMENT
ALL REQUIRED
PERFORMANCE METRICS
EXIT TO
CONSTRUCTION DOCUMENT PHASE
SUBMIT PHASE COMPLETION DOCUMENTS
FOR APPROVAL
PROJECT MANAGER:
REVIEW/DOCUMENT
ALL REQUIRED
PERFORMANCE METRICS
PHASE APPROVAL
EXIT TO
BIDDING AND PERMITTING PHASE
PROJECT MANAGER:
REVIEW/DOCUMENT
ALL REQUIRED
PERFORMANCE METRICS
EXIT TO
CONSTRUCTION ADMINISTRATIONPHASE
PROJECT MANAGER:
REVIEW/DOCUMENT
ALL REQUIRED
PERFORMANCE METRICS
EXIT TO
PROJECT CLOSEOUT PHASE
PROJECT MANAGER:
REVIEW/DOCUMENT
ALL REQUIRED
PERFORMANCE METRICS
END

## PROJECT NUMBER
PROJECT NUMBER REQUEST
(SUB-FLOW)
START
EXIT TO
WORKFLOW
DIAGRAM

## INITIATION PHASE
PROJECT INITIATION PHASE
(SUB-FLOW)
REQUIRED FOR DESIGN SCHEDULE
(NEED TO VERIFY)
REQUIRED FOR SERVICE ORDER
ESTABLISHES DESIGN MILESTONE
DELIVERY DATES FOR EACH PHASE
(REVISIONS MUST BE TRACKED)
REQUIRED FOR SERVICE ORDER
MUST BE LISTED AS PART
OF THE DOCUMENT
(REVISIONS MUST BE TRACKED)
REQUIRED FOR COMPLETION
OF COMPENSATION DATA FORM
TO BE INCLUDED IN THE
SERVICE ORDER
REQUIRED FOR COMPLETION
OF COMPENSATION DATA FORM
TO BE INCLUDED IN THE
SERVICE ORDER
REQUIRED FOR SERVICE ORDER
ESTABLISHES BASE FEE FOR
DESIGN SERVICES
(REVISIONS MUST BE TRACKED)
VERIFY THAT ACTUAL
AIA SERVICE ORDER WILL BE
COMPLETED BY OTHERS
START
REVIEW INITIAL INFORMATION
PROVIDED
DETERMINE
REQUIRED PHASES
DETERMINE
ADDITIONAL SERVICES /
SUPPLEMENTAL SERVICES
REQUIRED
EXIT TO DESIGN SCHEDULE
EXAMPLE
EXIT TO COMPENSATION DATA FORM
EXAMPLE
DETERMINE FEES FOR
ADDITIONAL SERVICES /
SUPPLEMENTAL SERVICES
REQUIRED
DETERMINE
REQUIRED
REIMBURSABLE
EXPENSES
COMPLETE
SERVICE ORDER TEMPLATE
(AIA B221-2018)
EXIT TO
SERVICE ORDER TEMPLATE
EXAMPLE
EXIT TO
WORKFLOW
DIAGRAM

## FEASIBILITY STAGE
FEASIBILITY STAGE
(SUB-FLOW)
REVIEW:
SCOPE
BUDGET
SCHEDULE
INFORMATION GATHERING
WITH END USER
IF REQUIRED
START
SCHEDULE / ATTEND
FEASIBILITY STAGE
KICK-OFF MEETING
SCHEDULE / ATTEND
FEASIBILITY STAGE
INTERNAL INTERVIEW
PRELIMINARY
PROGRAM
DEVELOPMENT
SCENARIO
DEVELOPMENT
EXIT TO
WORKFLOW
DIAGRAM
UTILIZATION
ANALYSIS
FEASIBILITY STAGE APPROVAL

## SITE PLANNING
SITE PLANNING SERVICES
(SUB-FLOW)
ARCHITECTURAL SITE PLAN
IS DEVELOPED FIRST
FURTHER DEVELOPMENT OF
ARCHITECTURAL SITE PLAN
START
RECEIVE INITIAL SITE INFORMATION
(CAD, REVIT OR PDF)
DOCUMENT VERIFICATION/
PLANNING & ZONING
REASEARCH
/
ARCHITECTURAL SITE PLAN DESIGN /
DOCUMENTATION
SCHEDULE
ARCHITECTURAL SITE PLAN
REVIEW MEETING
SCHEDULE/ATTEND
PROJECT KICK-OFF
MEETING
SITE PLAN APPROVAL
SCHEDULE PRELIMINARY SITE PLAN KICK-OFF MEETING
PLANNING & ZONING
REASEARCH TO MEET REQUIREMENTS OF THE AHJ
/
PRELIMINARY SITE PLAN DESIGN /
DOCUMENTATION
SCHEDULE
PRELIMINARY SITE PLAN
REVIEW MEETING
SITE PLAN APPROVAL
EXIT TO
WORKFLOW
DIAGRAM

## SD
SCHEMATIC DESIGN PHASE
(SUB-FLOW)
DETERMINE IF THIS IS THE
FIRST SITE VISIT
CONTRACT SAYS OTHERWISE
YES
NO
YES
NO
VERIFY: FIELD MEASUREMENT &
SITE DUE DILIGENCE REPORT
SERVICES ARE ADDITIONAL SERVICES
(RE: SCOPE OF WORK)
OR PROJECT MAY ONLY REQUIRE
"PROGRAMMING LITE"
START
SITE DUE DILIGENCE
INITIAL SITE VISIT
WITH CONSULTANTS
DOES THE OWNER HAVE AN EXISTING, ACCURATE SET OF CONSTRUCTION DOCUMENTS?
COORDINATE W/OWNER
SCOPE OF FIELD MEASUREMENTS SERVICES
(ADDITIONAL SERVICES)
DOES THE OWNER HAVE AN EXISTING CAD/REVIT FILE THAT COMPLY W/OWNER STANDARDS?
COORDINATE W/OWNER
SCOPE OF UPDATING/CREATING THE FILES
(ADDITIONAL SERVICES)
USING THE SITE DUE DILIGENCE CHECKLIST DEVELOP A SITE DUE DILIGENCE REPORT
DETAILED PROGRAMMING
SCHEDULE INTERVIEWS
REVIEW INFORMATION AS REQUIRED. OWNER MAY PROVIDE THIS INFORMATION
DEVELOP PRELIMINARY FLOOR PLAN(S) BASED ON AGREED UPON PROGRAM SUMMARY
PRELIMINARY FLOOR PLAN APPROVAL
DEVELOP SCHEMATIC DESIGN DOCUMENTS
PEER DESIGN REVIEW 1
EXIT TO
WORKFLOW
DIAGRAM
DOCUMENT ALL EXCEPTIONS TO DESIGN STANDARDS FOR APPROVAL
PRELIMINARY CODE REVIEW

## DD
DESIGN DEVELOPMENT PHASE
(SUB-FLOW)
ARCHITECT CANNOT PROCEED
TO CD PHASE WITH OUTSTANDING
EXCEPTIONS YET TO BE APPROVED
START
CREATE DESIGN DEVELOPMENT PACKAGE
W/CONSULTANTS
INCORPORATE / COORDINATE PACKAGE W/ALLIANCE PARTNERS
SCHEDULE PROGRESS REVIEW MEETING TO DISCUSS:
ARCHITECTURAL, FURNITURE, MEDICAL EQUIPMENT AND MILLWORK ELEVATIONS
QA/QC REVIEW 1
EXIT TO
WORKFLOW
DIAGRAM
DOCUMENT ALL EXCEPTIONS TO DESIGN STANDARDS FOR APPROVAL
PEER DESIGN REVIEW 2
SCHEDULE PROGRESS REVIEW MEETING TO DISCUSS:
POWER/DATA REQUIREMENTS, REVISIONS, ADDITIONS & DESIGN STANDARDS EXCEPTIONS
CONTINUE TO INCORPORATE / COORDINATE PACKAGE W/ALLIANCE PARTNERS
DEVELOP MEP NARRATIVE WITH CONSULTANTS
SCHEDULE REVIEW MEETING TO FINALIZE: POWER/DATA REQUIREMENTS, FINISHES, REVISIONS & DESIGN STANDARDS EXCEPTIONS

## CD
CONSTRUCTION DOCUMENT PHASE
(SUB-FLOW)
START
DEVELOP CONSTRUCTION DOCUMENT PACKAGE
W/CONSULTANTS
INCORPORATE / COORDINATE FINAL PACKAGE W/ALLIANCE PARTNERS
EXIT TO
WORKFLOW
DIAGRAM
PERFORM CLASH DETECTION
SCHEDULE 50% PROGRESS REVIEW MEETING
(GROUND UP PROJECTS ONLY)
QA/QC REVIEW 2
SCHEDULE 90% REVIEW MEETING
(AS REQUIRED BY OWNER)

## B&P
BIDDING AND PERMITING PHASE
(SUB-FLOW)
START
EXIT TO
WORKFLOW
DIAGRAM

## CA
CONSTRUCTION ADMINISTRATION PHASE
(SUB-FLOW)
START
EXIT TO
WORKFLOW
DIAGRAM

## CLOSEOUT
PROJECT CLOSEOUT PHASE
(SUB-FLOW)
START
EXIT TO
WORKFLOW
DIAGRAM